## Sheet1
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date | Number of Bugs
Bug | EMBEDDED-15 | 1.0.03 Peecee - Scratch with C-Macros - 180, 360, and Mini or DC motors Functions Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-03 03:02 | 2024-04-09 23:48 | 2023-11-25
Bug | EMBEDDED-17 | 1.0.03 Peecee - Scratch - Accelerometer & Gyro Function Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-04 02:03 | 2024-04-09 23:48 | 2023-11-25
Bug | EMBEDDED-26 | 1.0 Hexapod - Scratch - Ultrasonic sensor Function Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-06 23:43 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-27 | 1.0 Hexapod - Scratch - If Else condition Function Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 00:07 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-28 | 64, PeeCee V1, 1.0.02 firmware test-ultrasonic sensor/All UIs. | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 21:38 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-29 | 79, PEECEE V0.1-micropython/test on web-Overall issues | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 21:40 | 2023-12-14 02:36 | 2023-11-10
Bug | EMBEDDED-30 | 96, Peecee V1 C programming test/ servos EF. | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 21:42 | 2024-01-08 23:01 | 2023-12-04
Bug | EMBEDDED-31 | PLAYC-864 1.0 PeeCee - New Scratch C Bug ( Web) | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 21:43 | 2024-04-09 23:48 | 2023-12-04
Bug | EMBEDDED-32 | 1.0 PeeCee - MicroPython - Touchpad 2 & 3 Function Swapped- Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 21:57 | 2024-01-08 22:58 | 2023-12-04
Bug | EMBEDDED-33 | 1.0 Peecee - MicroPython - 180 Servo Motors E & F Ports Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:11 | 2024-04-09 23:49 | 2023-12-04
Bug | EMBEDDED-34 | 1.0 PeeCee - MicroPython - A2, B2, C2, E2, and F2 Ports i/p - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:17 | 2024-01-08 22:59 | 2023-12-04
Bug | EMBEDDED-35 | 1.0.03 PeeCee - C-MACROS - Hardware bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:19 | 2024-04-09 23:49 | 2023-12-04
Bug | EMBEDDED-36 | 1.0.03 PeeCee - Upload Issue | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:20 | 2023-11-08 22:11 | 2023-11-10
Bug | EMBEDDED-37 | 1.0.03 PeeCee C macros | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:21 | 2024-01-08 23:02 | 2023-12-04
Bug | EMBEDDED-38 | 0.1 PeeCee - RGB - Program Uploading - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:23 | 2024-01-10 02:45 | 2023-11-10
Bug | EMBEDDED-41 | 1.0.03 PeeCee - Hex Screen - RGB Program PeeCee Resetting - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:28 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-43 | 0.1 PeeCee - Flowchart Screen - RGB Enable Resetting - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:31 | 2024-01-10 02:47 | 2023-11-10
Bug | EMBEDDED-44 | 0.1 PeeCee - Hex Screen - Start Panel Counter Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:33 | 2024-01-10 02:50 | 2023-11-10
Bug | EMBEDDED-45 | 1.0 PeeCee - Hex Screen - Start panel - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:34 | 2024-01-11 04:06 | 2023-12-04
Bug | EMBEDDED-46 | 1.0.03 PeeCee - Hex Screen Start Panel - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:36 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-47 | 0.1 & 1.0 PeeCee - Hex&Flowchart Screen - WAIT Panel Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:37 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-48 | 0.1 PeeCee - Flowchart Screen - 4-1 sensor with any o/p Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:39 | 2024-01-08 22:57 | 2023-12-04
Bug | EMBEDDED-49 | 1.0.03 PeeCee - PC USB cable connection with Erase Button Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 22:41 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-50 | 1.0.03 PeeCee- Hex Screen - Plain Code Uploading Issue - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 23:03 | 2023-12-18 02:21 | 2023-12-04
Bug | EMBEDDED-51 | 1.0.03 PeeCee - Assemble page - Temp Value - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 23:06 | 2023-12-11 03:28 | 2023-12-04
Bug | EMBEDDED-52 | 91. 0.1zing-hex/create action-web | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 23:10 | 2024-07-17 06:36 | 2023-11-10
Bug | EMBEDDED-53 | 1.0 Zing - Assemble screen & Flowchart Decision panel - Digital & Analog Readings - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 23:41 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-54 | 0.1 & 1.0 Zing - Joystick - Walk Action - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-07 23:45 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-55 | 60. Product-Zing V1.0 Issue related to-M1,M2 and S1S2 Test on-Android Issue Type-Firmware | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:26 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-56 | 63. Product-zingV1.0 Issue related to-Hex>Repeat on loop Test on-Android Issue Type-Firmware | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:27 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-58 | 0.1 Zing - Assemble Screen - Hardware Bug | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:29 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-59 | 1.0 Zing - Hex page - if condition - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:31 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-60 | 1.0 Zing - Accelerometer & Gyro meter Readings - Hardware bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:33 | 2024-06-14 22:46 | 2023-11-11
Bug | EMBEDDED-61 | 1.0 Zing - Program Uploading Issue - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:34 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-62 | Hexapod - Joystick Screen - Feature; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:37 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-63 | 1.0 Hexapod - All Internal o/p & External o/p Components Functions - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:39 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-64 | 1.0 Hexapod - Hex Screen - If Else Condition Uploading Issue - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-08 00:42 | 2024-06-14 22:46 | 2023-11-10
Bug | EMBEDDED-66 | 1.0.03 PeeCee - Hex & Flowchart Screens - Buzzer Function - WEB & EXE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-09 04:18 | 2023-12-11 03:29 | 2023-12-04
Bug | EMBEDDED-67 | 0.1 PeeCee - Flowchart Screen - RGB Enable Resetting - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-12 21:52 | 2023-12-11 03:30 | 2023-12-04
Bug | EMBEDDED-68 | 0.1 PeeCee - Hex Screen - Start Panel Counter Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-12 22:06 | 2024-01-10 02:50 | 2023-11-17
Bug | EMBEDDED-72 | 1.0 Zing - Play mode - Camera screen All Commands Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-15 02:02 | 2024-06-14 22:46 | 2023-11-18
Bug | EMBEDDED-73 | 0.1 & 1.0 Zing - PA Reading Screens - Battery % - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-15 05:25 | 2024-06-14 22:46 | 2023-11-18
Bug | EMBEDDED-74 | 1.0 Zing - Hex Screen - Action group Function - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-15 05:46 | 2024-06-14 22:46 | 2023-11-18
Bug | EMBEDDED-75 | 1.0 PeeCee - Scratch - M1, M2, M3 & M4 ports Rename - Hardware Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-17 04:13 | 2024-04-09 23:49 | 2023-12-04
Bug | EMBEDDED-76 | 1.0 PeeCee - Play Mode - Accept n no of PLAY bytes | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-17 04:15 | 2023-12-18 02:20 | 2023-12-04
Bug | EMBEDDED-137 | 1.0 Zing - Scratch - M1, 2, 3 & 4 ports Function - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-24 02:18 | 2024-06-14 22:46 | 2023-12-01
Bug | EMBEDDED-138 | 1.0 Zing - Scratch - 180 & 360 Servo Motors B1-port Function - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-24 03:34 | 2024-06-14 22:46 | 2023-12-01
Bug | EMBEDDED-139 | 1.0 Zing - MicroPython - i/p & o/p programs Uploading Function - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-25 02:17 | 2024-06-14 22:46 | 2023-12-01
Bug | EMBEDDED-140 | 1.0 Zing - MicroPython - RGB Function - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-25 02:41 | 2023-12-06 23:10 | 2023-12-01
Bug | EMBEDDED-141 | 1.0 Zing - Micro-Python - Serial Servo motors Functions - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-25 04:19 | 2024-01-18 22:34 | 2023-11-30
Bug | EMBEDDED-147 | 1.0 PeeCee - New Micropython Buzzer Function - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-27 05:20 | 2023-12-14 02:37 | 2023-12-04
Bug | EMBEDDED-149 | 1.0 Zing - All PA Bytes Reading Screens - Ultrasonic Function: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-28 22:58 | 2024-06-14 22:46 | 2023-12-08
Bug | EMBEDDED-150 | 1.0 Zing - Micro Python - Analog Components PA Bytes Range - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-29 21:55 | 2023-12-14 01:16 | 2023-12-08
Bug | EMBEDDED-151 | 1.0 Zing - Micro-python - Gyro Meter Function: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-29 23:40 | 2023-12-14 01:19 | 2023-12-08
Bug | EMBEDDED-152 | 1.0 Zing - Hex Screen - Action Group - Break Dance Function; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-11-30 00:24 | 2024-06-14 22:46 | 2023-12-08
Bug | EMBEDDED-185 | 1.0 Zing - Hex Screen - Mini & Dc Motors Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-04 03:30 | 2024-06-14 22:46 | 2023-12-08
Bug | EMBEDDED-187 | 1.0 PeeCee - Scratch with C-Macros - Dc & Mini Motors - M1, M2 Ports Enabling - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-04 23:27 | 2024-04-09 23:49 | 2023-12-04
Bug | EMBEDDED-189 | 1.0.04 PeeCee - All PA Bytes Reading Screens - TOuchpad 03 Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-05 01:09 | 2023-12-18 02:20 | 2023-12-04
Bug | EMBEDDED-190 | 1.0.04 PeeCee - Status LED - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-05 03:22 | 2023-12-18 02:17 | 2023-12-04
Bug | EMBEDDED-191 | 1.0.04 PeeCee - PA Bytes Reading - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-05 04:15 | 2023-12-18 02:17 | 2023-12-04
Bug | EMBEDDED-194 | 1.0.04 PeeCee -Hex & Flowchart Screen - External o/p Components Uploading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-06 00:19 | 2023-12-18 02:17 | 2023-12-04
Bug | EMBEDDED-195 | 1.0.04 PeeCee - Internal & External components Input PA Bytes Reading Function -HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-06 03:18 | 2023-12-18 02:08 | 2023-12-09
Bug | EMBEDDED-257 | 1.0 Zing - Create Action Screen - Save to Zing Functions - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-11 04:36 | 2024-07-09 00:02 | 2023-12-20
Bug | EMBEDDED-265 | 1.0 PeeCee - Micro-Python - Internal Eye RGB Functions - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-13 03:06 | 2024-01-18 04:57 | 2023-12-22
Bug | EMBEDDED-266 | 1.0 PeeCee - Micro-python - Touch Pad 0 Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-14 02:15 | 2024-04-09 23:50 | 2023-12-15
Bug | EMBEDDED-267 | 1.0.04 PeeCee - Status LED Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-15 03:04 | 2023-12-28 02:14 | 2023-12-22
Bug | EMBEDDED-268 | 1.0.04 PeeCee - Hex & Flowchart Screen - Internal RGBs Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-15 05:37 | 2023-12-26 01:59 | 2023-12-22
Bug | EMBEDDED-317 | 1.0 Zing - Firmware[Features Testing] Entire Play Screen - Functions - Hardware Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2023-12-22 02:36 | 2024-06-14 22:46 | 2023-12-29
Bug | EMBEDDED-318 | 1.0 Zing - Firmware[Features Testing] - All PA Bytes Reading Screens & Functions - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-22 03:13 | 2024-06-14 22:46 | 2023-12-29
Bug | EMBEDDED-319 | 1.0 Zing - Firmware [Features Testing] - Serial Servos and Programs uploading Functions - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2023-12-22 04:17 | 2024-06-14 22:46 | 2023-12-29
Bug | EMBEDDED-333 | 1.0.04 PeeCee - Data Graph - Internal & External i/p Readings Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-02 00:50 | 2024-01-11 03:19 | 2024-01-05
Bug | EMBEDDED-335 | 1.0.04 PeeCee - PA Bytes Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-02 02:56 | 2024-01-11 04:06 | 2024-01-05
Bug | EMBEDDED-336 | 1.0.04 PeeCee - Hex & Flowchart Screen - F1 Port Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-04 05:06 | 2024-01-11 03:37 | 2024-01-12
Bug | EMBEDDED-337 | 1.0.04 PeeCee - Joystick Screen - RGB Eyes Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-06 03:10 | 2024-01-11 04:05 | 2024-01-12
Bug | EMBEDDED-349 | 0.1 PeeCee - Hex Screen - Internal RGB with Pause Button Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-12 02:13 | 2024-04-27 04:42 | 2024-01-19
Bug | EMBEDDED-355 | 1.0 Zing - Micro-Python - Serial Servo Motor program upload Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-18 06:13 | 2024-04-09 23:50 | 2024-01-26
Bug | EMBEDDED-360 | 1.0.04 PeeCee - Hex Screen - Internal o/p RGB with Pause Button Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-24 02:09 | 2024-04-02 00:45 | 2024-01-26
Bug | EMBEDDED-361 | 1.0.04 PeeCee - Assemble Screen - PA Reading Functions - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-25 01:42 | 2024-02-27 02:23 | 2024-01-27
Bug | EMBEDDED-362 | 1.0.04 a & b Firmware Release Testing - Assemble Screen - Interna i/p color Sensor Readings & Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-31 06:04 | 2024-02-27 02:26 | 2024-02-03
Bug | EMBEDDED-363 | 1.0.04 a & b Firmware Release Testing - Assemble Screen, Hex & Flowchart screens - All internal & External PA Readings Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-31 06:26 | 2024-02-27 02:32 | 2024-02-03
Bug | EMBEDDED-364 | 1.0.04 Firmware Release Testing - Data Mode - Internal Sensors & Ports Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-31 06:40 | 2024-02-27 02:35 | 2024-02-03
Bug | EMBEDDED-365 | 1.0.04 Firmware Release Testing - Play panel - Music Screen - PeeCee tone mode Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-01-31 06:46 | 2024-04-01 02:36 | 2024-02-03
Bug | EMBEDDED-369 | 1.0 Zing - Micro Python -File Explore Build -Project Run or File Run - RGB colour Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-02 23:14 | 2024-04-09 23:46 | 2024-02-10
Bug | EMBEDDED-370 | 1.0.04 PeeCee - Joystick Screen - RGB Eyes Function - Hardware Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-03 02:06 | 2024-04-01 02:38 | 2024-02-10
Bug | EMBEDDED-380 | 1.0.02 Zing - Firmware Testing - Joystick Screen - Dance Actions Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-07 02:52 | 2024-06-14 22:46 | 2024-02-10
Bug | EMBEDDED-535 | 1.0.02 Zing - Firmware Testing - Joystick Screen - Current Running Programs Stop Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-15 05:50 | 2024-06-14 22:46 | 2024-02-24
Bug | EMBEDDED-547 | 1.0.02 Zing - Firmware Testing - Hex Screen - o/p Action Group - Box Forward Function - WEB Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-16 04:24 | 2024-06-14 22:46 | 2024-02-24
Bug | EMBEDDED-550 | 1.0 Zing - Micro-Python - Serial Servo motors Functions - HARDWARE Bug; | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-17 04:38 | 2024-04-09 23:46 | 2024-02-24
Bug | EMBEDDED-590 | 1.0 Zing - Micro-Python - Firmware & WEB Build Testing - Accele & Gyro meters Program Function - WEB Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-02-26 02:16 | 2024-04-09 23:47 | 2024-03-02
Bug | EMBEDDED-653 | Zing V1.0.02 - UX Function - All Reading Screen - All External i/p Analog Sensor Readings - Maximum Range values Displayed - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-21 04:35 | 2024-06-14 22:46 | 2024-03-28
Bug | EMBEDDED-660 | Zing V1.0.02 - UX Function - Hex & Flowchart Screens - 1C & 2C LEDs o/p Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-25 01:44 | 2024-06-14 22:46 | 2024-04-01
Bug | EMBEDDED-661 | Zing V2.0.01 - UX Function - All PA Bytes Reading Screen - EYE Ultrasonic Sensor Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-25 05:12 | 2024-06-14 22:46 | 2024-04-01
Bug | EMBEDDED-662 | Zing V1.0.02 & 2.0.01 S3 - UX Function - Speech Panel - Dance-Stop Command & Dance, Stop Commands Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-25 22:29 | 2024-06-14 22:46 | 2024-04-02
Bug | EMBEDDED-663 | PeeCee - V1.0.04 - Release Testing - UX Function - Hex & Flowchart Screens - Internal o/p Buzzer Frequency Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-26 22:28 | 2024-03-26 23:12 | 2024-04-03
Bug | EMBEDDED-664 | Zing V1.0.02 - UX Function - All PA Bytes Reading Screens - C-port Ultrasonic sensor PA Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-26 23:27 | 2024-06-14 22:46 | 2024-04-03
Bug | EMBEDDED-665 | Zing V2.0.01 S3 - UX Function - All PA Bytes Reading Screens - PA Bytes Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-03-31 23:10 | 2024-06-14 22:46 | 2024-04-08
Bug | EMBEDDED-666 | 1.0.04 PeeCee - Hex Screen - Internal o/p RGB with Assemble Screen Read Value Button Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-02 00:50 | 2024-04-09 23:50 | 2024-04-09
Bug | EMBEDDED-670 | Zing V 0.1, 1.0.02 & 2.0.01 S3 - UX Function - All PA Bytes Reading Screens - Battery% Function -HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-02 02:35 | 2024-06-14 22:46 | 2024-04-09
Bug | EMBEDDED-671 | Zing V2.0.01 S3- UX Function - Hex & Flowchart Screen - Internal 2 RGB Eyes Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-02 05:03 | 2024-06-14 22:46 | 2024-04-09
Bug | EMBEDDED-672 | Zing V2.0.01 - UX Function - Hex & Flowchart Screens - Head Motor Uploading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-02 05:22 | 2024-06-14 22:46 | 2024-04-09
Bug | EMBEDDED-673 | Hexapod V 1.0.01 32 & 2.0.01 S3 - UX Function - Hex & Flowchart Screen - All PA Bytes Reading Screens - Accelerometer & Gyro-meter Reading & UI Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-04-04 22:49 | 2024-06-14 22:46 | 2024-04-12
Bug | EMBEDDED-675 | Hexapod V2.0.01 S3 Board - UX Function - All PA Bytes Reading Screens - All External i/p Digital Components A2-port Reading Function A1 port - HARDWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-04-05 00:29 | 2024-06-14 22:46 | 2024-04-12
Bug | EMBEDDED-676 | Hexapod V2.0.01 S3 board - UX Function - Create Action Motors Functions & Zing Save Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-04-05 01:33 | 2024-06-14 22:46 | 2024-04-12
Bug | EMBEDDED-677 | Roboki 0.2.01V - UX Function - Hex Screen - Program uploading Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Highest | Done | Done | 2024-04-05 05:05 | 2024-04-27 04:28 | 2024-04-12
Bug | EMBEDDED-678 | Roboki 0.2.01V - UX Function - Hex Screen - Internal o/p RGB Color Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-05 05:20 | 2024-04-27 04:28 | 2024-04-12
Bug | EMBEDDED-681 | Roboki 0.2.01V - UX Function - Assemble Screen - B2 port Analog External Components Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-08 03:58 | 2024-04-27 04:28 | 2024-04-15
Bug | EMBEDDED-682 | Roboki 0.2.01 V - UX Function - Assemble & Hex Screen - Ultrasonic Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-08 04:19 | 2024-04-27 04:52 | 2024-04-15
Bug | EMBEDDED-683 | Roboki 0.2.01 V - UX Function - Hex Screen - DC & Mini Motors M1 - port Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-09 04:24 | 2024-04-27 04:30 | 2024-04-16
Bug | EMBEDDED-687 | Zing V2.0.01 S3 - UI & UX Function - Joystick Screen - All Action Buttons UI & UX Function - WEB & HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-10 03:13 | 2024-06-14 22:46 | 2024-04-17
Bug | EMBEDDED-688 | Zing 2.0.01 S3 V - UX Function - All PA Bytes Reading Screens - Accelerometer X & Y Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-04-10 22:35 | 2024-06-14 22:46 | 2024-04-18
Bug | EMBEDDED-690 | Robiki 0.2.01 V - UX Function - Hex Screen - 360 Servo Motors Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-11 00:38 | 2024-04-27 04:54 | 2024-04-18
Bug | EMBEDDED-691 | Zing 2.0.01 S3 V - UX Function - All PA Bytes Reading Screens - All PA Bytes Reading Function - WEB & HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-13 03:46 | 2024-06-14 22:46 | 2024-04-20
Bug | EMBEDDED-692 | Hexapod V1.0 - 32, UX & UI Function - Joystick Screen - Dance Button Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-15 02:32 | 2024-06-14 22:46 | 2024-04-22
Bug | EMBEDDED-693 | Hexapod V-1.0.02 32 - UX Function - Assemble & Hex Screen - Battery Maximum % Values Display Issue - HARDWAREBug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-15 22:40 | 2024-06-14 22:46 | 2024-04-23
Bug | EMBEDDED-694 | Hexapod V-1.0.02 - 32 Board - UX Function - Hex Screen - DC & Mini Motors M1& M2 - ports Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-16 23:36 | 2024-11-05 02:53 | 2024-04-24
Bug | EMBEDDED-695 | Hexapod V-1.0.02 32 Board - UX Function - Hex Screen - All o/p Programs Functions Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-17 04:58 | 2024-06-14 22:46 | 2024-04-24
Bug | EMBEDDED-698 | Hexapod V-1.0.02 - 32 Board - UX Function - Hex Screen - M1 & M2 Port Functions Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-23 04:24 | 2024-06-14 22:46 | 2024-04-30
Bug | EMBEDDED-703 | Hexapod V- 1.0.02 32 Board - UX Function - Hex Screen - 360 Servo Motor Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-23 05:17 | 2024-06-14 22:46 | 2024-04-30
Bug | EMBEDDED-711 | Zing 1.0.02 & 2.0.01, Hexapod -1.0.02 - UX Function - Hex Screen - Internal o/p Action Group Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-25 05:33 | 2024-06-14 22:46 | 2024-05-02
Bug | EMBEDDED-715 | Zing V- 2.0.01 S3 Board - UX Function - Hex Screen - Action Group Box Forward Action Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-29 03:42 | 2024-06-14 22:46 | 2024-05-07
Bug | EMBEDDED-717 | Zing V - 1.0.02 32 Board - UX Function - All PA Reading Screens - All Digital i/p Components Reading Function - HARDWARE Bug | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-30 03:03 | 2024-06-14 22:46 | 2024-05-08
Bug | EMBEDDED-718 | Hexapod 1.0.02 - 32 Board - UX Function - All PA Reading Screens - All Digital i/p Components Reading Function - HARDWARE Bug | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-04-30 03:06 | 2024-06-14 22:46 | 2024-05-08
Bug | EMBEDDED-748 | Zing 1.0.02 32 Board - UX Function - Hex Screen - Internal o/p RGB Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-07 02:58 | 2024-06-14 22:46 | 2024-05-14
Bug | EMBEDDED-750 | Zing 2.0.01 S3 Board - UX Function - Hex Screen - Internal o/p Left 1st RGB Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-07 03:19 | 2024-06-14 22:46 | 2024-05-14
Bug | EMBEDDED-752 | Hexapod 2.0.01 S3 Board V - UX Function - Hex Screen - Internal i/p & o/p If else Condition Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-08 00:45 | 2024-06-14 22:46 | 2024-05-15
Bug | EMBEDDED-754 | PeeCee - V - 1.0.05 - UX Function - Hex Screen - All Motors Combination if else Condition Programs Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-05-09 01:15 | 2024-05-10 21:19 | 2024-05-16
Bug | EMBEDDED-755 | Hexapod V - 2.0.01 - UX Function - All PA Bytes Reading Screens - B2 port All Analog External Components Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-09 03:04 | 2024-06-14 22:46 | 2024-05-16
Bug | EMBEDDED-759 | Hexapod 1.0.02 32 Board - UX Function - Hex Screen - Internal i/p Ultrasonic Sensor Reading Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-11 02:20 | 2024-06-14 22:46 | 2024-05-18
Bug | EMBEDDED-760 | Hexapod 1.0.02 32 Board - UX Function - Hex Screen - Internal o/p Left & Right (6) RGBs Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-11 02:48 | 2024-06-14 22:46 | 2024-05-18
Bug | EMBEDDED-761 | Hexapod - 1.0.02 32 Board - UX Function - Hex Screen - Internal o/p RGB with External all o/p COmponents Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-11 04:25 | 2024-06-14 22:46 | 2024-05-18
Bug | EMBEDDED-765 | Hexapod V - 2.0.01 S3 Board - UX Function - All PA Bytes Reading Screen - All Internal, External i/p & o/p PA Bytes Reading Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-13 05:42 | 2024-06-14 22:46 | 2024-05-20
Bug | EMBEDDED-770 | Zing V- 1.0.1.0 32 Board - UX Function - Hex Screen - Head Servo motor Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-17 02:00 | 2024-06-14 22:46 | 2024-06-28
Bug | EMBEDDED-775 | PeeCee V - 1.0.0.6 -UX Function - Hex Screen - Internal i/p Light Sensor with Internal & External any o/p's Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-24 00:01 | 2024-05-27 02:08 | 2024-05-31
Bug | EMBEDDED-776 | PeeCee - V - 1.0.06 - UX Function - Internal i/p Colour Sensor with Internal or External o/p's if-else Condition Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-24 00:05 | 2024-05-27 02:07 | 2024-05-31
Bug | EMBEDDED-777 | Roboki V - 1.0.1.0 - UX Function - Hex Screen - Double if-else Condition of Internal i/p with External all Motors Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-25 03:46 | 2024-05-27 03:06 | 2024-06-01
Bug | EMBEDDED-778 | Roboki V - 1.0.1.0 - UX Function - Hex Screen - Double if-else Condition of Internal i/p with External all Motors Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-25 03:51 | 2024-05-27 03:13 | 2024-06-01
Bug | EMBEDDED-783 | Hexapod V- 2.0.01 S3 Board - UX Function - All PA Bytes Screen - All PA Bytes Reading Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-05-29 06:03 | 2024-06-14 22:46 | 2024-06-05
Bug | EMBEDDED-796 | Roboki V -1.0.1.0 - UX Function - Hex Screen - Mini & DC Motors Functions Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-06 00:17 | 2024-11-05 02:54 | 2024-06-13
Bug | EMBEDDED-798 | Zing 2.0.01 S3 Board - UX Function - Create Action 1 Action Block Play Button Functions Issue -HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-07 04:26 | 2024-06-14 22:46 | 2024-06-14
Bug | EMBEDDED-799 | Zing 2.0.01 S3 Board - UX Function - Create Action - Head Motor Functioning Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-07 22:41 | 2024-06-19 06:03 | 2024-06-15
Bug | EMBEDDED-800 | Hexapod - 2.0.01 S3 Board - UI Function - Create Action Screen - Saved File Display Issue - WEB Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-08 02:46 | 2024-06-21 05:17 | 2024-06-15
Bug | EMBEDDED-801 | Zing 2.0.01 S3 Board - UX Function - Create Action Screen - Saving any program Zing Restarting Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-08 05:35 | 2024-06-21 22:54 | 2024-06-15
Bug | EMBEDDED-803 | Zing & Hexapod V - 1.0 & 2.0 - UX Function - Hex Screen - A2 port o/p External Components Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-11 23:51 | 2025-02-17 21:16 | 2024-06-19 | 1
Bug | EMBEDDED-804 | Zing & Hexapod V- 2.0 S3 Board - UX Function - Hex Screen - Double if condition Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-12 03:48 | 2024-06-22 00:12 | 2024-06-19
Bug | EMBEDDED-844 | Hexapod 2.0.1.0 - UX Function - All PA Bytes Reading Screens - B1 port Analog Components Reading Function - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-22 03:46 | 2024-06-26 05:41 | 2024-06-29
Bug | EMBEDDED-845 | Hexapod 1.0 & 2.0 - UX Function - Joystick Screen - Slide LEFT & RIGHT Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-26 01:05 | 2024-06-26 05:01 | 2024-07-03
Bug | EMBEDDED-847 | Hexapod 1.0.1.0 - UX Function - Joystick Screen - One Action in-between Other Action Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-27 05:03 | 2024-06-27 05:36 | 2024-07-04
Bug | EMBEDDED-848 | Zing 2.1.2.0 Firmware - UX Function - iOS Mobile Firmware detecting Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-28 04:42 | 2024-07-08 06:06 | 2024-07-05
Bug | EMBEDDED-849 | Zing 2.0 & 2.1 Firmwares - UX Function - Hex Screen - Group Action-Wake Front, Bow, & Squat Actions Function Issue - HARDWARE Bug | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-28 05:58 | 2024-07-08 06:05 | 2024-07-05
Bug | EMBEDDED-850 | Zing 2.0.1.0 Firmware - UX Function - All PA Bytes Reading Screens - Internal i/p Ultrasonic Sensor Reading Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-28 06:09 | 2024-07-10 22:50 | 2024-07-05
Bug | EMBEDDED-851 | Zing, Hexapod - 1.0 & 2.0 - UX Function - Hex Screen - Serial servo motor function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-06-29 01:24 | 2024-07-10 23:30 | 2024-07-06
Bug | EMBEDDED-872 | create servo limiters - for each servo | Nikhil Robinson | bibox hardware | Medium | Done | Done | 2024-07-03 19:21 | 2024-08-11 23:52 | 2024-07-04
Bug | EMBEDDED-873 | kLAW - play bytes / actions NOT working - sort / release them | Nikhil Robinson | bibox hardware | Medium | Done | Done | 2024-07-03 19:23 | 2024-07-11 05:58 | 2024-07-04
Bug | EMBEDDED-874 | redesign - klaw servo wiring at assembly | Pavvan Varma | bibox hardware | Medium | Done | Done | 2024-07-03 19:28 | 2024-07-08 22:02 | 2024-07-05
Bug | EMBEDDED-876 | lewan soul vs dS servo motor - read angle comparison - demo to Sandeep sir | Nikhil Robinson | bibox hardware | Medium | Done | Done | 2024-07-03 19:32 | 2024-07-11 05:58 | 2024-07-06
Bug | EMBEDDED-877 | zing - box - foam sheet cut - 60mm | Pavvan Varma | bibox hardware | Highest | Done | Done | 2024-07-03 21:15 | 2024-07-10 00:02 | 2024-08-15
Bug | EMBEDDED-878 | hexapod / crawler v2.0 - foam sheet cut - 60mm | Pavvan Varma | bibox hardware | Highest | Done | Done | 2024-07-03 21:19 | 2024-07-10 00:01 | 2024-08-15
Bug | EMBEDDED-924 | KLAW 1.0 - UX Function - All PA Bytes Reading Screens - All Analog Components Reading Function - HARDWARE Bug: | bibox hardware | NareshKumar | Medium | Done | Done | 2024-07-16 03:16 | 2024-11-12 02:00 | 2024-07-23 | 1
Bug | EMBEDDED-925 | KLAW 1.0.1.0 Firmware - UX Function - Hex Screen - if-else condition on B1 Port with A1 port o/p Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-07-16 05:42 | 2024-08-23 01:31 | 2024-07-23 | 1
Bug | EMBEDDED-933 | KLAW 1.0.1.0 Device - UX Function - All PA Bytes Reading Screens - 6 Pot sensors reading Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-07-19 01:42 | 2024-11-05 02:52 | 2024-07-26 | 2
Bug | EMBEDDED-934 | KLAW 1.0.1.0 Firmware - UX Function - Hex Screen - Decision Panel Program uploading Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-07-19 03:37 | 2024-11-05 02:53 | 2024-07-26 | 1
Bug | EMBEDDED-936 | KLAW 1.0.1.0 Device - UX Function - Port's Power Issue - HARDWARE Bug: | bibox hardware | NareshKumar | Medium | Done | Done | 2024-07-19 06:13 | 2024-12-18 04:52 | 2024-07-26 | 3
Bug | EMBEDDED-1013 | PeeCee 1.0 - UX Function - Hex Screen - 180 & 270 Servo Motors Slider Function Issue - Firmware Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-06 01:33 | 2024-08-23 00:59 | 2024-08-13 | 1
Bug | EMBEDDED-1015 | PeeCee 1.0 - UX Function - Hex Screen - 360 Servo Motors Slider Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-06 03:32 | 2024-10-22 03:35 | 2024-09-17 | 1
Bug | EMBEDDED-1016 | Zing & Hexapod 1.0 & 2.0 - UX Function - Hex Screen - 180, 270, & 360 Servo Motors Live write Slider Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-06 06:10 | 2024-08-23 00:57 | 2024-08-13 | 1
Bug | EMBEDDED-1033 | Hexapod 1.0 & 2.0 - UX Function - Joystick Screen - 2nd & 3rd serial servo motor Function Issue - Firmware Bug: | Nikhil Robinson | NareshKumar | Medium | On HOLD |  | 2024-08-13 03:19 | 2024-10-01 04:11 | 2024-11-12 | 2
Bug | EMBEDDED-1035 | PeeCee 1.0 - UX Function - Hex Screen - Live write with o/p LEDs Function Issue - HARDWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-16 03:07 | 2024-09-07 00:30 | 2024-08-23 | 1
Bug | EMBEDDED-1045 | PeeCee 1.0 - UX Function - Hex Screen - DC, N20 & Dynamex Motors Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-16 22:52 | 2024-08-28 01:30 | 2024-08-24 | 1
Bug | EMBEDDED-1051 | Hexapod 2.0 - UI & UX Function - Create Action - Saved Program Delete Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-20 22:46 | 2024-08-28 00:31 | 2024-08-28 | 1
Bug | EMBEDDED-1052 | PeeCee 1.0 (AI-1) - UI & UX Function - App-Mode Hardware Screen - Bluetooth function Issue - FIRMWARE Bugs: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-08-22 03:22 | 2024-08-28 22:22 | 2024-08-29 | 2
Bug | EMBEDDED-1054 | PeeCee 1.0 Ai-1 - UX Function - Hex Screen - OLED o/p Text Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-08-24 02:50 | 2024-09-07 00:31 | 2024-08-31 | 1
Bug | EMBEDDED-1055 | KLAW 1.0 - UX Function - Joystick Screen - Attention position Function issue - FIRMWARE Bug: | NareshKumar | NareshKumar | Medium | Done | Done | 2024-08-24 04:49 | 2024-08-29 06:17 | 2024-08-31 | 1
Bug | EMBEDDED-1075 | All Device All Versions - UX Function - All PA Reading Screens - External Digital Components PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-09-10 05:01 | 2024-09-18 06:26 | 2024-09-17 | 1
Bug | EMBEDDED-1089 | Roboki 1.0.2.0 - UX Function - All PA Bytes Reading Screens - Ultrasonic A-port PA Reading Function Issue - HARDWARE Bug: | bibox hardware | NareshKumar | Medium | Done | Done | 2024-09-11 07:02 | 2025-02-18 01:19 | 2024-09-18 | 1
Bug | EMBEDDED-1090 | Zing 2.0 - UX Function - Joystick & Speech Screen - Slide Left & Right Kick & Front Right & Left Kick Function Swiped Issue - Firmware Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-09-12 05:35 | 2024-09-18 06:25 | 2024-09-19 | 1
Bug | EMBEDDED-1094 | Roboki 1.0 - UX Function - All PA Reading Screen - Internal & External Components i/p's PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-09-18 05:55 | 2024-09-20 02:25 | 2024-09-25 | 1
Bug | EMBEDDED-1196 | Hexapod 1.0 & 2.0 - UX Function - Joystick Screen - 3 Actions Attention Position Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-10-28 05:05 | 2024-10-30 01:14 | 2024-11-04 | 1
Bug | EMBEDDED-1197 | Zing 1.0 & 2.0 - UX Function - Joystick Screen - Push-up Action After Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-10-28 05:44 | 2024-10-30 03:01 | 2024-11-04 | 1
Bug | EMBEDDED-1210 | ATR_H2 - UX Function - Hex Screen - Internal o/p Motors with Plain Program Function Issue - HARDWARE Bug: | bibox hardware | NareshKumar | High | Done | Done | 2024-11-04 21:57 | 2025-02-20 04:20 | 2024-11-12 | 1
Bug | EMBEDDED-1211 | ATR_H2 - UX Function - Hex Screen - Internal o/p Motor "Live write" Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-11-04 23:49 | 2025-02-20 04:20 | 2024-11-12 | 1
Bug | EMBEDDED-1243 | PeeCee 1.0 - UX Function - Assemble Screen - Ultrasonic External Component PA Bytes Reading Function Issue - Firmware Issue: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-11-09 04:02 | 2024-11-12 02:08 | 2024-11-16 | 1
Bug | EMBEDDED-1263 | Toki 1.0 - UX Function - Assemble Screen - Read Button Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-11-15 03:24 | 2024-12-19 01:33 | 2024-11-22 | 1
Bug | EMBEDDED-1280 | Klaw 1.0 - UX Function - Hex Screen - PWM 5th Servo Motor Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-11-27 04:36 | 2024-11-29 01:33 | 2024-12-04 | 1
Bug | EMBEDDED-1285 | KLAW-1.0 - UX Function - Hex screen - B-port If-else Condition function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2024-11-29 00:05 | 2024-11-29 01:35 | 2024-12-06 | 1
Bug | EMBEDDED-1291 | ATR-H2 - UX Function - Bluetooth Connectivity Issue - HARDWARE Bug: | bibox hardware | NareshKumar | High | Done | Done | 2024-12-03 04:57 | 2025-02-20 04:21 | 2024-12-10 | 1
Bug | EMBEDDED-1298 | Zing 2.1.4.0- Latest Firmware - UX Function - Create Action Save File Issue - HARDWARE Big: | bibox hardware | NareshKumar | Medium | Done | Done | 2024-12-05 04:20 | 2025-07-17 02:43 | 2024-12-12 | 1
Bug | EMBEDDED-1299 | Zing 2.1.4.0 - Latest Firmware - UX Function - Joystick Screen - Zing Struck Issue - FIRMWARE Issue: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-05 04:33 | 2024-12-05 22:59 | 2024-12-12 | 1
Bug | EMBEDDED-1300 | Zing 2.1.4.0 - Latest Firmware - UX Function - All PA Reading Screens - Ultrasonic sensor PA Reading Function Issue - FIRMWARE Issue: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-05 05:40 | 2024-12-10 01:01 | 2024-12-12 | 1
Bug | EMBEDDED-1307 | Toki - UX Function - Assemble & Hex Screen - DC/N20 Motors Function & Live Write Function Issue - FIRMWARE Bugs: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-06 02:32 | 2024-12-18 03:45 | 2024-12-13 | 2
Bug | EMBEDDED-1321 | Zing 2.0 Latest Firmware (2.4) - UF Function - Operation Mode UI & Function Bytes Issue - FIRMWRE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-10 00:02 | 2024-12-10 03:32 | 2024-12-17 | 1
Bug | EMBEDDED-1322 | All Devices Latest Firmware - UX Function - Hex Screen - Start panel Bi-Data Program Not Functioning - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-10 03:51 | 2025-03-25 00:16 | 2025-01-29 | 1
Bug | EMBEDDED-1323 | Zing 2.0 Latest Firmware 2.04 - UX Function - Data Panel Issue - FIRMWARE Bugs: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-11 01:55 | 2025-02-09 23:22 | 2024-12-18 | 1
Bug | EMBEDDED-1330 | Zing 2.0 Latest Firmware (2.4) - UX Function - Hex Screen - Head ultrasonic RGB Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-17 23:21 | 2024-12-30 22:04 | 2024-12-25 | 1
Bug | EMBEDDED-1331 | TOKI 1.0 - UX Function - Assemble Screen - o/p's gets Struck Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-18 03:31 | 2024-12-19 01:31 | 2024-12-25 | 1
Bug | EMBEDDED-1333 | Klaw 1.0 - UX Function - Hex Screen - Serial Servo 5th motor Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Highest | Done | Done | 2024-12-20 02:06 | 2025-06-25 23:58 | 2024-12-27 | 2
Bug | EMBEDDED-1336 | Klaw 1.0 - UX Function - Hex Screen - Ultrasonic sensor with any o/p (if-else) Program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-20 04:41 | 2025-02-18 01:18 | 2024-12-27 | 1
Bug | EMBEDDED-1338 | Toki 1.0 - UX Function - Any Screen - Bluetooth Connectivity Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2024-12-25 00:44 | 2025-01-16 02:13 | 2025-01-01 | 1
Bug | EMBEDDED-1341 | Zing 2.0 Latest Firmware (2.0.4.0) - UX Function - Hex Screen - Head ultrasonic Right RGB Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | BUGS |  | 2024-12-30 22:50 | 2025-02-17 21:35 | 2025-01-07 | 1
Bug | EMBEDDED-1370 | Toki 1.0 - UX Function - Hex Screen - Servo Motors Function Issues - FIRMWARE Bug: | Nikhil Robinson | Nareshkumar | Medium | Done | Done | 2025-01-16 02:28 | 2025-07-17 02:40 | 2025-01-23 | 1
Bug | EMBEDDED-1371 | PeeCee 1.0 Ai Latest Firmware - UX Function - Hex Screen - Program Upload Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Highest | Done | Done | 2025-01-17 22:39 | 2025-01-19 22:45 | 2025-01-25 | 1
Bug | EMBEDDED-1375 | KLAW 1.0 - UX Function - All PA Reading Screen - PA Read Button Function Iaaue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-01-18 02:58 | 2025-06-26 | 2025-01-25 | 1
Bug | EMBEDDED-1376 | PeeCee 1.0 Ai-1 - UX Function - Hex Screen - Ai-1 Music with Stop Panel Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-01-19 23:17 | 2025-01-21 04:29 | 2025-01-27 | 2
Bug | EMBEDDED-1378 | PeeCee 1.0 Ai-1 - UX Function - Hex Screen - Ai-1 i/p with OLED Program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-01-20 02:57 | 2025-02-09 23:23 | 2025-01-27 | 1
Bug | EMBEDDED-1379 | PeeCee Ai-1 - UX Function - Hex Screen - Combination of Ai trained Program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-01-20 04:49 | 2025-02-10 02:00 | 2025-01-27 | 2
Bug | EMBEDDED-1407 | Toki 1.0 - UX Function - All PA Reading Screen - Digital i/p PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-01-28 03:05 | 2025-02-09 23:20 | 2025-02-04 | 1
Bug | EMBEDDED-1433 | Roboki 0.2 V- UX Function- Hex Screen - DIP Switch & LED Toggle Function issue- HARDWARE Bug | Nikhil Robinson | Surabhi S | Medium | Done | Done | 2025-02-04 21:16 | 2025-02-18 01:04 | 2025-02-19 | 1
Bug | EMBEDDED-1434 | Roboki 0.2 V- UX Function- Hex Screen - Dual Switch & Double LED 2C Toggle Function - HARDWARE Bug: | Nikhil Robinson | Surabhi S | Medium | Done | Done | 2025-02-04 22:53 | 2025-02-18 01:03 | 2025-02-19 | 1
Bug | EMBEDDED-1459 | Zing 2.0 - UX Function - Free Fall Detection & Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-06 03:47 | 2025-02-17 21:36 | 2025-02-13 | 1
Bug | EMBEDDED-1460 | PeeCee 1.0 - UX Function - Hex Screen - Without Satisfying Condition the o/p Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-06 04:28 | 2025-02-17 21:48 | 2025-02-13 | 1
Bug | EMBEDDED-1461 | PeeCee 1.0 Ai- 1 - UX Function - Hex Screen - Ai-1 Music Display Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-08 02:12 | 2025-02-10 02:00 | 2025-02-15 | 1
Bug | EMBEDDED-1462 | PeeCee 1.0 Ai-1 - UX Function - Asemble & Hex Screens - Ai-1 Lidar PA Reading Functionality Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-08 03:47 | 2025-02-10 02:47 | 2025-02-15 | 3
Bug | EMBEDDED-1463 | PeeCee Ai-1 - UX Function - Hex Screen - Colour Train with o/p Functioning Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-09 23:53 | 2025-03-25 04:51 | 2025-02-17 | 1
Bug | EMBEDDED-1464 | PeeCee 1.0 Ai-1 - UX Function - Hex Screen - Speech with Music if-else Condition program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-10 03:17 | 2025-02-12 21:59 | 2025-02-17 | 1
Bug | EMBEDDED-1465 | Roboki 1.0.2.0 - UX Function - Hex Screen - Counter Condition program function issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-11 04:06 | 2025-02-12 01:08 | 2025-02-18 | 1
Bug | EMBEDDED-1466 | PeeCee 1.0 Ai-1 - UX Function - Hex screen - Ai-1 Color Detection, Tracking & Face Tracking PA Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-12 22:13 | 2025-03-25 04:52 | 2025-02-20 | 1
Bug | EMBEDDED-1471 | Zing 2.0 Ai-1 - UX Function - Hex Screen - Ai-1 PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-14 23:10 | 2025-02-18 01:02 | 2025-02-22 | 2
Bug | EMBEDDED-1472 | All Device Ai-1 - UX Function - Hex Screen - Face Tracking Y PA Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-17 02:02 | 2025-02-20 04:21 | 2025-02-24 | 1
Bug | EMBEDDED-1473 | All Devices - UX Function - Assemble Screen - o/p's functions with PA Read value Button & Hardware MD Button Functions Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-24 | 2025-03-25 05:04 | 2025-03-03 | 1
Bug | EMBEDDED-1474 | ATR-H2 - UX Function - Hex Screen - M3 Motor Live Write Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-02-24 23:02 | 2025-05-21 05:19 | 2025-03-04 | 1
Bug | EMBEDDED-1475 | ATR-H2 - UX Function - All PA Reading Screens - ATH Restarting Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-02-27 01:16 | 2025-04-21 00:38 | 2025-03-06 | 1
Bug | EMBEDDED-1476 | Crawle - 2.0 - UX Function - All PA Reading Screens - Ultrasonic Component Connection to C-port PA Reading & Restart Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-10 22:16 | 2025-03-25 05:06 | 2025-03-18 | 1
Bug | EMBEDDED-1477 | Zing 2.0 - UX Function - Play panel All Screens - Free Fall Action Performing Issue - FIRMWARE. Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-11 01:31 | 2025-07-14 02:28 | 2025-03-18 | 1
Bug | EMBEDDED-1487 | MOKI 1.0 - UI & UX Function - Hex Screen - 180, 270, & 360 Servo motors function Issue - Firmware Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-12 03:25 | 2025-03-25 06:09 | 2025-03-19 | 1
Bug | EMBEDDED-1488 | All Device - Ai-1 - UX Function - Face Train Screen - Trained Face Response Not Updating on Application Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-03-12 04:52 | 2025-03-25 05:26 | 2025-03-19 | 1
Bug | EMBEDDED-1489 | All Devices Ai-1 - UX Function - Hex Screen - 2 Mic Condition with 2 Audio Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-13 03:59 | 2025-07-17 02:41 | 2025-03-20 | 1
Bug | EMBEDDED-1490 | MOKI 1.0 - UX Function - Hex Screen(action panel) - Live Output Function Not Working for Ports M1 and M2 - Firmware Bug: | Nikhil Robinson | Surabhi S | High | Done | Done | 2025-03-14 01:14 | 2025-03-25 05:23 | 2025-03-28 | 1
Bug | EMBEDDED-1491 | Roboki, Zing, Crawl-e, Klaw, & ATR - UX Function - All PA Reading Screens - AI-1 with All i/p's PA Readings Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-19 23:17 | 2025-03-25 05:27 | 2025-03-27 | 1
Bug | EMBEDDED-1492 | Zing, Crawl-e 2.0 - UX Function Issue - All PA Reading Screens - Internal & External Ultrasonic Sensor PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-20 23:06 | 2025-07-14 02:45 | 2025-03-28 | 1
Bug | EMBEDDED-1493 | ATR-H2 Ai-1 - UX Function - Hex Screen - Ai-1 Face Recognition PA Text Not Display Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-21 03:28 | 2025-03-25 05:49 | 2025-03-28 | 1
Bug | EMBEDDED-1496 | CLONE - Toki 1.0 - UX Function - Hex Screen - Servo Motors Function Issues - FIRMWARE Bug: 2 | Nikhil Robinson | Surabhi S | Medium | TESTING / Review |  | 2025-03-25 04:45 | 2025-04-09 05:52 | 2025-01-23 | 1
Bug | EMBEDDED-1497 | CLONE - MOKI 1.0 - UI & UX Function - Hex Screen - 180, 270, & 360 Servo motors function Issue - Firmware Bug: 2 | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-25 06:06 | 2025-04-21 00:36 | 2025-03-19 | 1
Bug | EMBEDDED-1498 | ATR_H2 - UX Function - All PA Reading Screens - ATR Restart Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | BUGS |  | 2025-03-26 00:43 | 2025-06-15 21:50 | 2025-04-02 | 1
Bug | EMBEDDED-1499 | Zing 2.0 - UX Function - Micro-python - ACCELEROMETER and GYRO meter program Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-27 05:42 | 2025-05-16 02:59 | 2025-04-03 | 1
Bug | EMBEDDED-1500 | Zing & Crawl-e 2.0 - UX Function - Micro-Python Environmental - Serial Servo Motors Functioning Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | TESTING / Review |  | 2025-03-29 03:55 | 2025-06-13 03:34 | 2025-04-05 | 1
Bug | EMBEDDED-1501 | Crawl-e 2.0 - UX Function - Micro-Python Environment - import library Name Zing Calling Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-03-29 04:19 | 2025-05-16 04:21 | 2025-04-05 | 1
Bug | EMBEDDED-1502 | ATR_H2 - UX Function - Firmware Updating Tool - ATR_H2 Firmware Not Present In the Site Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | High | Done | Done | 2025-04-01 00:32 | 2025-04-21 00:37 | 2025-04-08 | 1
Bug | EMBEDDED-1518 | KLAW 1.0 - UX Function - Scratch & Hex Screen - Internal i/p Pot with Any O/P's Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-04-14 06:17 | 2025-06-26 00:06 | 2025-04-21 | 1
Bug | EMBEDDED-1519 | Moki - UX Function - Hex Screen - DC & N20 motors Program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | TESTING / Review |  | 2025-04-19 01:00 | 2025-05-15 03:24 | 2025-04-26 | 1
Bug | EMBEDDED-1521 | PeeCee 1.0 - UX Function - Micro-Python Screen - I/P Touch pad Read Values Printing Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-02 02:16 | 2025-05-16 04:23 | 2025-05-09 | 1
Bug | EMBEDDED-1522 | Klaw 1.0 - UX Function - Micro-Python Screen - Ultrasonic Sensor PA Reading Printing Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-02 04:21 | 2025-05-16 05:35 | 2025-05-09 | 1
Bug | EMBEDDED-1523 | PeeCee & Klaw 1.0 - UX Function - Micro-Python Screen - OLED Text Printing Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-04 23:57 | 2025-05-21 05:13 | 2025-05-12 | 1
Bug | EMBEDDED-1524 | PeeCee 1.0 - UX Function - Micro-Python Environment - Proximity & ADC Reading Example code Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-06 01:35 | 2025-05-21 05:00 | 2025-05-13 | 2
Bug | EMBEDDED-1525 | PeeCee 1.0 - UX Function - Micro-Python Environment - Gesture Sensor Values not printing - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-06 02:03 | 2025-05-21 05:00 | 2025-05-13 | 1
Bug | EMBEDDED-1526 | Zing & Hexapod 2.0 Latest Boards - UX Function - All PA Reading Screen - Accelerometer & Gyrometer (QMI) PA Reading Issue - HARDWARE Bug: | bibox hardware | NareshKumar | High | BUGS |  | 2025-05-08 03:13 | 2025-05-08 03:13 | 2025-05-15 | 1
Bug | EMBEDDED-1527 | Zing & Hexapod 2.0 Latest Board - UX Function - Micro-python Environmental - RGB-Ultrasonic Program Uploading Function & PA Reading Printing Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | TESTING / Review |  | 2025-05-08 03:51 | 2025-06-13 03:35 | 2025-05-15 | 3
Bug | EMBEDDED-1528 | All Devices - UX Function - Teachable Machine Control Screen - Camera working reverse angle Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-14 03:31 | 2025-06-10 04:37 | 2025-05-21 | 1
Bug | EMBEDDED-1529 | All Devices - UI & UX Functions - Hex Screen - Ai-1 PA Read Disconnect Ai-1 Error Handling Issue Features - FIRMWARE: | Nikhil Robinson | NareshKumar | Medium | TESTING / Review |  | 2025-05-19 06:12 | 2025-05-22 05:21 | 2025-05-26 | 1
Bug | EMBEDDED-1530 | All Devices Ai-1 - UX Function - Hex Screen - Colour Detection Green & Blue if else condition Not Functioning Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-20 06:08 | 2025-05-28 22:58 | 2025-05-27 | 1
Bug | EMBEDDED-1531 | PeeCee 1.0 - UX Function - Hex Screen Face & Color Tracking PA Reading Not Functioning & Struck Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-22 05:40 | 2025-06-15 22:14 | 2025-05-29 | 2
Bug | EMBEDDED-1532 | PeeCee 1.0 Ai-1 - UX Function - Hex Screen - Ai-1 Face Tracking PA Reading Not Functioning Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-05-28 02:07 | 2025-06-15 22:15 | 2025-06-04 | 1
Bug | EMBEDDED-1533 | All Devices Ai-1 - UX Function - Hex Screen - Colour Tracking PA Reading Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-06-11 05:52 | 2025-06-15 22:16 | 2025-06-18 | 1
Bug | EMBEDDED-1534 | All Devices Ai-1 - UX Function - Hex Screen - Face Tracking Pa Reading Not Functioning Issue - FIRMWARM Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-06-12 02:31 | 2025-06-15 22:16 | 2025-06-19 | 1
Bug | EMBEDDED-1535 | All Devices Ai-1 - UX Function - Hex Screen - Colour Tracking with Speech Combination Program Function Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | Done | Done | 2025-06-12 06:08 | 2025-07-14 02:50 | 2025-06-19 | 1
Bug | EMBEDDED-1536 | All Devices Ai-1 - UX Function - Hex Screen - Ai-1 Camera Function Issue - HARDWARE Bug: | bibox hardware | NareshKumar | Medium | BUGS |  | 2025-06-12 06:31 | 2025-06-12 06:31 | 2025-06-19 | 1
Bug | EMBEDDED-1538 | Zing 3.0 - UX Function - Joystick Screen - Side Left & Right Kick Action Not Functioning Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | BUGS |  | 2025-06-30 00:56 | 2025-08-14 02:36 | 2025-07-07 | 1
Bug | EMBEDDED-1542 | All Devices - UX Function - Upcoming Firmware Update Tool - Variant, Extra Robki Firmware, & Nightly Release Date Info Issue - FIRMWARE Bug: | Nikhil Robinson | NareshKumar | Medium | BUGS |  | 2025-07-01 06:43 | 2025-08-13 05:15 | 2025-07-08 | 4
Bug | EMBEDDED-1593 | Toki - UX Function - Hex Screen - S2 Port Function Swap Issue - FIRMWARE Bug: | Nikhil Robinson | Nareshkumar | Highest | BUGS |  | 2025-08-05 02:49 | 2025-08-05 22:44 | 2025-08-12 | 1
Bug | EMBEDDED-1594 | IR Sensor PA Reading Not Function Issue | Nikhil Robinson | Nareshkumar | Medium | BUGS |  | 2025-08-07 06:22 | 2025-08-19 01:15 | 2025-08-14 | 1
Bug | EMBEDDED-1596 | First dance song plays 3-4 seconds longer after completion. | bibox hardware | Nareshkumar | High | BUGS |  | 2025-08-11 23:01 | 2025-08-13 01:15 | 2025-08-19 | 1
Bug | EMBEDDED-1609 | PeeCee 1.0 - UX Function - New & Old Enverinmental - 2nd & 3rd Touchpads functionality Swipes - FIRMWARE Bug: | Nikhil Robinson | Nareshkumar | High | BUGS |  | 2025-08-27 02:55 | 2025-08-27 02:55 | 2025-09-05 | 1
Bug | EMBEDDED-1620 | Klaw-b - UI/UX Function - Dance Actions, Manual Mode Text, 90° Position, and Delete Action Feature (Firmware Bugs) | Nikhil Robinson | Nareshkumar | Medium | Done | Done | 2025-09-02 06:41 | 2025-09-04 22:37 | 2025-09-11 | 3
Bug | EMBEDDED-1621 | CLONE - Klaw-b - UI/UX Function - Manual Mode Text, and Label Feature (Firmware Bugs) 2 | Nikhil Robinson | Nareshkumar | Medium | BUGS |  | 2025-09-04 22:36 | 2025-09-04 22:38 | 2025-09-16 | 2